## Cost Breakdown
Category | Item | Qty | Unit Price (INR) | Subtotal (INR) | Source / Note
Compute | ESP32-S3-DevKitC-1 (N16R8) | 1 | 1100 | 1100 | Global list price ~$12 (Walmart/eBay), +India import/reseller markup
Sensing | MPU9250 9-DOF IMU breakout | 1 | 350 | 350 | Budget route - software sensor fusion on ESP32; BNO085/055 (Rs1500-4000) is the pricier alternative
Propulsion | 1800KV brushless motor (2204-2206 class) | 1 | 750 | 750 | Matches XTR-33 designer's suggested combo
Propulsion | 20-30A BLHeli ESC | 1 | 550 | 550 | Matches XTR-33 designer's suggested combo
Propulsion | 8x4.3 propeller (pack incl. spares) | 1 | 200 | 200
Power | 3S LiPo battery (850-1300mAh) | 1 | 850 | 850 | Sized for a ~150-250g flying weight
Control surfaces | Servos: 1x9g + 2x2.3g micro | 1 | 1000 | 1000 | Matches XTR-33 designer's suggested combo
RC link | ExpressLRS nano receiver (2.4GHz) | 1 | 1700 | 1700 | Global ~$17-19 (eBay) + India landing cost
Fabrication | LW-PLA filament (1 spool) | 1 | 3000 | 3000 | Foaming filament - required for the printed weight target
Fabrication | Standard PLA filament (1 spool) | 1 | 800 | 800 | Structural/non-critical printed parts
Fabrication | TPU filament (1 spool) | 1 | 1000 | 1000 | Control-surface hinges; can substitute tape hinges to cut this
Logging | MicroSD module + card (8GB) | 1 | 300 | 300 | Onboard black-box logging
Misc | Wiring, connectors, control horns, glue, hardware | 1 | 700 | 700 | Bundled allowance
| PROTOTYPE #1 SUBTOTAL |  |  | 12300
Tooling (one-time) | Entry FDM 3D printer (if no campus/ThrustMIT access) | 1 | 16000 | 16000 | Skip this row entirely if ThrustMIT/college fab lab covers printing
Tooling (one-time) | LiPo charger (if not already owned) | 1 | 1500 | 1500 | Skip if already owned from prior RC/rocketry work
Tooling (one-time) | Full ELRS TX+RX radio system (if starting from scratch) | 1 | 5000 | 5000 | Skip if a compatible transmitter is already owned
| ONE-TIME TOOLING SUBTOTAL (contingent - see notes) |  |  | 22500
| GRAND TOTAL (assuming tooling already available) |  |  | 12300
Assumptions
Exchange rate used where only USD prices were found: ~Rs 88 / USD (verify at time of purchase - this moves).
Assumes ThrustMIT / campus fab lab covers 3D printing (filament cost only, no printer purchase).
Assumes an ELRS-compatible transmitter and a LiPo charger are already owned from prior RC/rocketry work.
Camera module for Stage 5 vision work is deliberately excluded - Stages 1-4 (this prototype's target) don't need it; add ~Rs 500-700 when Stage 5 starts.
Prices are current best estimates from live listings (see research_log.xlsx for sources) - re-check before ordering.

## Timeline
Phase | What happens | Start Date | Duration (weeks) | End Date | Notes
A - Software build | Finish jsbsim_env, aerodynamics, reward, curriculum, train, evaluate, emergency, vision, stats, knowledge base, dashboard | 2026-08-27 | 7 | 2026-10-15 | Continuing the current one-file-at-a-time build
B - Procurement + printing | Order electronics, print XTR-33 parts, assemble airframe | 2026-09-15 | 6 | 2026-10-27 | Runs in parallel with the back half of Phase A
C - Sim training (Stages 1-4) | Stabilization, navigation, takeoff, landing curriculum stages in JSBSim | 2026-10-15 | 5 | 2026-11-19 | Mostly unattended compute time once launched
D - Odd-sem exams / buffer | Reduced hands-on pace; let Stage 5-6 sim training run in background | 2026-11-20 | 5 | 2026-12-25 | Matches your Nov-Dec exam pattern - training doesn't need active attention
E - Hardware bring-up | ESP32 firmware, sensor calibration, ground bench tests, telemetry range check | 2026-12-21 | 3 | 2027-01-11 | Semester break - good window for hands-on hardware work
F - Policy distillation | Shrink trained SAC policy to a TFLite-Micro model, flash to ESP32, SIL/HIL testing | 2027-01-10 | 2 | 2027-01-24
G - First real flights | Manual airworthiness check with safety pilot, then supervised autonomous handoff | 2027-01-26 | 5 | 2027-03-02 | Keep a manual override switch at every flight
H - Real-data iteration | Log real flight data, retrain/fine-tune in sim to close the sim-to-real gap, reflash, retest | 2027-03-01 | 4 | 2027-03-29
I - Even-sem exams / buffer | Reduced hands-on pace again | 2027-04-01 | 6 | 2027-05-13 | Matches your April-May exam pattern
J - Validation flights | Demonstrate autonomous stabilization + navigation + at least one resilience scenario (e.g. simulated GPS loss) | 2027-05-16 | 4 | 2027-06-13 | This is the 'working prototype' milestone
K - Docs + IP + funding prep | Decide repo visibility, file provisional patent, DPIIT recognition, identify a DISC challenge to target | 2027-06-16 | 4 | 2027-07-14 | Do this before wider public disclosure of the methodology
Buffer | Safety margin before the July deadline | 2027-07-14 | 2 | 2027-07-28 | Hardware/RL projects slip - this is intentional, not padding you should cut
Formulas:
End Date = [Start Date]+[Duration (weeks)]*7

## Task Checklist
Category | Task | Status
Technical | Finish jsbsim_env.py, aerodynamics.py (with real XTR-33 coefficients), reward.py, curriculum.py | Not started
Technical | Finish train.py, evaluate.py, emergency.py, vision.py, stats.py | Not started
Technical | Build knowledge base scraper/indexer/retriever and the dashboard | Not started
Technical | Distill trained SAC policy into a TFLite-Micro model sized for ESP32-S3 | Not started
Technical | Write ESP32 firmware: sensor read, control loop, telemetry, SD logging, RTH failsafe | Not started
Procurement | Order ESP32-S3, MPU9250, motor, ESC, prop, battery, servos, ELRS receiver | Not started
Procurement | Source LW-PLA, PLA, and TPU filament | Not started
Procurement | Confirm 3D printing access (ThrustMIT/campus fab lab) or budget a printer | Not started
Fabrication | 3D print XTR-33 outdoor variant parts | Not started
Fabrication | Assemble airframe, install electronics, balance CG | Not started
Testing | Ground bench test: motor/ESC/servo response, IMU calibration, telemetry range | Not started
Testing | First manual test flights with a safety pilot for airworthiness | Not started
Testing | Supervised autonomous handoff flights | Not started
Testing | Log real flight data and run retrain/reflash iteration cycles | Not started
Regulatory | Confirm LoRa/ELRS firmware is set to the India 865-867 MHz region plan | Not started
Regulatory | Check DGCA UAS rules for this aircraft's weight class before outdoor flights | Not started
IP / Funding | Decide whether the GitHub repo stays public or goes private before wider disclosure | Not started
IP / Funding | File a provisional patent once the first working demonstrator flies | Not started
IP / Funding | Get DPIIT Startup India recognition | Not started
IP / Funding | Identify an upcoming DISC edition (autonomous systems / surveillance) and prep the application | Not started